## Sheet1
Login Page:
1)In Login Page: Password must be set limit | done | min 6,max10
Role Management:
2)Role Management-In role List: While clicking the add button, save the role code and role name, status is automatically changed 'Active'.now click the edit button, see the status field, status is'Inactive'. | not applicable
3)Role Management-In role List: 'Organization level' should be mantatory for first time adding the role list. | done
4)Role Management-In role List:while adding the Duplicate record in Role List, data not displaying on Grid but Follwoing message displayed "saved successfully" | done
5)Role Management-In role List: While deleteing the some record on the grid, after try to create a same name record or new record, now click the save button, save button is not working and data is not adding.
6)(Once Refresh) Role Management-In role List:While adding the new record, onece after delete the record, -role_code -role_name -status_inactive -org_platform Click the save button, Following message are displayed "Successfully saved", but new record not displaying on role list grid. (note: status is inactive,save not working) | done | only showing active record
User Management:
1)While click the adding button, and click the direct save button for checking the validation message displayed or not. save button is not displayed validate message.
2)While adding the user list with 'Add' and 'Modify' check box is fully filled, and saved successfully, now click the edit button, view the 'add' and 'modify' check box is empty. | not applicable
3)While adding the user list, filling the all data with click save button, user list saved successfully, now click the edit button, change the 'UserName' and click save button, saved successfully, Click the view button, 'Username' not changed.(click URL refresh only worked) | done
4)While delete one the user list record(UserVSAccess), try to add the new Record with same re-Username, click the save button, following message are displayed "User Code cannot be duplicated". (Once click URL Refresh, page is working) | done | ok
SetUp & Master: Quick Code Maintenece:
1)While adding Valid Value details without 'Master code' and 'Master Description', click the save button, following message dispalyed "Master Definition Details saved successfully". not saving on Grid. | done
2)While adding 'Master code' and 'Master Description'with Valid Value details and click the save button, following message dispalyed "Master Definition Details saved successfully". data not saving on Grid. | done
3)While adding without 'value' and 'master details',click the save button, following message displayed "Master Definition Details saved successfully". | done
4)While click the min page adding(+) button,and clicking the subpage of 'master maintenance' adding (+) button(multiple time or single time), click the delete button on grid ---showing confirm message displayed "Are you sure you want to Delete this record?" ---click 'yes' button ---following message are displayed "Master Definition Deleted successfully" --and multiple duplicate Value added on grid | done
Farmer List:
1)While click the view icon in Farmer List, Click One by one Farmer Land Details, Land Barcode Details and Soil Details Viewed successfully. - Just Click the Other Farmer List Details. -and again click the old Farmer Land Details or other Farmer Land Details. all Land Details is empty.
KIOSK Set up:
1)While clicking the add button, Fill the below Fields, -kisok name -Address -Billingual Language -Pinode -Village -FPO Name and Without Status Field, click the save button, message displayed "saved successfully'. Now Open the View and Edit Button, Kiosk setup Page Data is empty. | done
2)Kiosk Set up - Automatically attachment is added without user manual. | done
3)While adding the notes from Edit button, below popup message displayed, Address filed should be filled up first. | not applicable
4)While adding Kiosk Contact Details from Edit, Filling all Mandatory fields, Click Save button, Following message displayed "Kiosk Set up Contact Details saved successfully " But Contact Details Data not displaying on Grid. | not applicable
5)While adding the duplicate record, Save button should be display Validation message.
Content Management-Soil Card
1)While choose 'Analysis Started On' and 'Analysis Completed On ' check whether end date is greater than or equal to start date | done
2)While adding the sample collection, Filling the all data and click the save button, showing success message displayed. Record not displayed on grid, and searching the add data, grid is empty | done | record moved ro checker
3)While click the edit button, change or update the data in fileds and click the save button, save button is not working | done | only rejected cases to edit
4)While adding the soild card attachemnt successfully uploaded. Click the edit button Soil card attachement is not uploded | done | attachment only for view in checker
5)While deleting the Soil Card Record, Following message displayed "Soil Card data Inactive successfully", But Page is not refreshing. Click the Overall Page Refresh, deleted Soil Card record is not display on Grid | done
Training videos