## Front_Page
Test Case Sheet
A) Document Details
Doc. ID :
Project Name :
Task ID :
Type of Testing : Unit / Integration/ System / Acceptance |  |  | <- Enter one or more, as applicable
* SRS Name/Version :
* FDS Name/Version :
B) Revision History
Rev. No. | Rev. Date | Revision Description | Prep. By | Revd. By | App By
C) Assumptions and Constraints
Note: List down various assumptions and constraints in writing and executing the test cases in terms of data non-availability or processes external to the application, which is not transperant and hence cannot be tested
Sr. | Assumptions and Constraints

## Case History
Test Case History
Test Iteration | 1 | 2 | 3 | 4 | 5
Build/Version | http://169.38.82.131:810/ | http://169.38.82.131:810/ | http://169.38.82.131:810/
Executed By | Uma | Uma | Uma
Executed Date | 5-5-21 | 6-5-21 | 7-5-21
Additional Test Cases | 20 | 5 | 5
Reviewed By
Review Date
Comments

## WPR
Work Product Review Sheet
Type of Review:
Date of Review:
Phase: |  | Testing
Revision No | Review / Track No | Review comments | Severity | Type of Defect | Phase Attribution | Disposition Action | Status | Posted by | Posted Date
Fields with blue colored test is to be filled by personnel who prepares the work product

## Case Sheet
Case Sheet
Sl. No | Test Case ID | Module Name | User Story | Test Description | Valid & Invalid Inputs | Expected Output | Actual Output | Test Result | Defect Priority | Defect Severity | Bug ID | Phase Attributed | Type of Defects | Disposition Action | Bug Status | Remarks / Screen Shot /Suggestions | Development Team Status | Development Team Remarks | Fixed By | Fixed Date | Tester
1 | KIOSK-001 | Login Page |  | Check Password field, wheather Password Textbox limit set or not |  | Password Field should be set limit | Password field allowed to length of character or number | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07 | Uma
2 | KIOSK-002 | Role Management-In role List: |  | Check Status Field, whether working properly or not |  | Active/Inactive should be work | While clicking the add button, save the role code and role name, status is automatically changed 'Active'.now click the edit button, see the status field, status is'Inactive'. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07 | Uma
3 | KIOSK-003 | Role Management-In role List |  | Check Organization Level, Organization Level Dropdown is mantatory or not |  | Organization level' should be mantatory | While Click the save button without 'Organization level', save button is not allowed | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07 | Uma
4 | KIOSK-004 | Role Management-In role List |  | Check duplicate record allowed or not in Role list |  | Duplicate Record should not be allow | while adding the Duplicate record in Role List, data not displaying on Grid but Follwoing message displayed "saved successfully" | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
5 | KIOSK-005 | Role Management-In role List |  | Check save button is working or not, after delete record |  | Save button should be work | While deleteing the some record on the grid, after try to create a same name record or new record, now click the save button, save button is not working and data is not adding. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
6 | KIOSK-006 | Role Management |  | Check Staus is Inactive,check once delete the record after the record is saved or not |  | Status is Inactive , savee button should be work | (Once Refresh) Role Management-In role List:While adding the new record, onece after delete the record, -role_code -role_name -status_inactive -org_platform Click the save button, Following message are displayed "Successfully saved", but new record not displaying on role list grid. (note: status is inactive,save not working) | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
7 | KIOSK-007 | User Management |  | Check Save button, wheather save button validate message display or not |  | Save button should be display validate message | While click the adding button, and click the direct save button for checking the validation message displayed or not. save button is not displayed validate message. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  |  | 2021-05-07
8 | KIOSK-008 | User Management |  | Check Edit Button, Add And Modify checkbox Properly diplay or not |  | Add And Modify checkbox Properly diplay while click on edit | While adding the user list with 'Add' and 'Modify' check box is fully filled, and saved successfully, now click the edit button, view the 'add' and 'modify' check box is empty. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  |  | 2021-05-07
9 | KIOSK-009 | User Management |  | Check Save/Edit and Update is whether properly working or not and page is refreshing or not |  | Update should be work | While adding the user list, filling the all data with click save button, user list saved successfully, now click the edit button, change the 'UserName' and click save button, saved successfully, Click the view button, 'Username' not changed.(click URL refresh only worked) | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
10 | KIOSK-010 | User Management |  | Check delete and add, while delete the record, again add the new record allowing or not. |  | Add a new record should be allow | While delete one the user list record(UserVSAccess), try to add the new Record with same re-Username, click the save button, following message are displayed "User Code cannot be duplicated". (Once click URL Refresh, page is working) | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
11 | KIOSK-011 | SetUp & Master: Quick Code Maintenece: |  | Check Without Master code and Master Description, record saved or not |  | Save button should be work with Validation | )While adding Valid Value details without 'Master code' and 'Master Description', click the save button, following message dispalyed "Master Definition Details saved successfully". not saving on Grid. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
12 | KIOSK-012 | SetUp & Master: Quick Code Maintenece: |  | Check Master code and Master Description, and Valid Value Details, wheather record is saved or not |  | Save button should be work with Validation | While adding 'Master code' and 'Master Description'with Valid Value details and click the save button, following message dispalyed "Master Definition Details saved successfully". data not saving on Grid. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
13 | KIOSK-013 | SetUp & Master: Quick Code Maintenece: |  | Check without Valid Value Details, wheather record is saved or not |  | Save button shour be display validation message | While adding without 'value' and 'master details',click the save button, following message displayed "Master Definition Details saved successfully". | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
14 | KIOSK-014 | SetUp & Master: Quick Code Maintenece: |  | Check Duplicate record allowed or not |  | Duplicate Record should not be allow | )While click the min page adding(+) button,and clicking the subpage of 'master maintenance' adding (+) button(multiple time or single time), click the delete button on grid ---showing confirm message displayed "Are you sure you want to Delete this record?" ---click 'yes' button ---following message are displayed "Master Definition Deleted successfully" --and multiple duplicate Value added on grid | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
15 | KIOSK-015 | Farmer List |  | Check Land Details is empty or not |  | Land Details should not be empty. | )While click the view icon in Farmer List, Click One by one Farmer Land Details, Land Barcode Details and Soil Details Viewed successfully. - Just Click the Other Farmer List Details. -and again click the old Farmer Land Details or other Farmer Land Details. all Land Details is empty. | Fail | Low | Minor |  |  |  |  | Open |  | Open
16 | KIOSK-016 | KIOSK Set up |  | Check View and Edit button,whether Kiosk setup Page Data empty or not |  | Kiosk setup Page Data should not be empty. | While clicking the add button, Fill the below Fields, -kisok name -Address -Billingual Language -Pinode -Village -FPO Name and Without Status Field, click the save button, message displayed "saved successfully'. Now Open the View and Edit Button, Kiosk setup Page Data is empty. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
17 | KIOSK-017 | KIOSK Set up |  | Check attachement, file automatically added or not |  | Kiosk setup attachement should not be automattically add | Kiosk Set up - Automatically attachment is added without user manual. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
18 | KIOSK-018 | KIOSK Set up |  | Check notes data, click save button is adding first or not |  | Notes should be add | While adding the notes from Edit button, below popup message displayed, Address filed should be filled up first. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
19 | KIOSK-019 | KIOSK Set up |  | Check Edit Button, Contact Details data is displaying or not |  | Contact Details Data should be display on Grid from Edit | While adding Kiosk Contact Details from Edit, Filling all Mandatory fields, Click Save button, Following message displayed "Kiosk Set up Contact Details saved successfully " But Contact Details Data not displaying on Grid. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
20 | KIOSK-020 | KIOSK Set up |  | Check duplicate record displaying or not |  | Validation message should be display | While adding the duplicate record, Save button should be display Validation message. | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-07
21 | KIOSK-021 | Content Management-Soil Card |  | Check 'Analysis Started On' and 'Analysis Completed On ' date format |  | Date Format should be display corrctly | While choose 'Analysis Started On' and 'Analysis Completed On ' check whether end date is greater than or equal to start date | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
22 | KIOSK-022 | Content Management-Soil Card |  | Check sample collection, whether save button is working or not and Gri displaying or not |  | Save button should be work and grid should be display a data | While adding the sample collection, Filling the all data and click the save button, showing success message displayed. Record not displayed on grid, and searching the add data, grid is empty | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
23 | KIOSK-023 | Content Management-Soil Card |  | Check edit button, check update the data, save button is working or not |  | Save button should be work | While click the edit button, change or update the data in fileds and click the save button, save button is not working | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
24 | KIOSK-024 | Content Management-Soil Card |  | Check attachement from edit, Soil card attachement is uplode or not |  | Soil card Attachment should be work from edit | While adding the soild card attachemnt successfully uploaded. Click the edit button Soil card attachement is not uploded | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
25 | KIOSK-025 | Content Management-Soil Card |  | Checking delete soil card record, page refreshing or not |  | Page should be refresh | While deleting the Soil Card Record, Following message displayed "Soil Card data Inactive successfully", But Page is not refreshing. Click the Overall Page Refresh, deleted Soil Card record is not display on Grid | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-07
26 | KIOSK-026 | Comtent Management: Training Videos: |  | Check save button whether save button is working or not |  | Save button shoule be work with Data | Training Videos: -Click the Add Button -Click Save Button without data entires and videos -Following message displayed "Training Videos Saved Successfully" | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-10
27 | KIOSK-027 | Comtent Management: Training Videos: |  | Check save button whether save button is working or not |  | save button should be work | Open the Edit Button in Training video without Entries or videos -Click the View Icon -Choose Upload button -Upload the Video without Entries -Click Save button -Save button not working | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | venkatachalam | 2021-05-10
28 | KIOSK-028 | Comtent Management: Training Videos: |  | Edit/Delete and clear is working or not |  | Video name should be clear | Open the Edit Button or New Add Button in Training video -Click the Cancel icon -Video is Deleted -Open Edit button -Video name is not cleared | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-10
29 | KIOSK-029 | Comtent Management: Training Videos: |  | Check duplicates allowing or not |  | Duplicate Record should not be allow | Open the Training video -Duplicate should not be allowed | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-10
30 | KIOSK-030 | Govertment Schemes |  | Check delete button is working or not |  | [object Object] should not be display | Govertment Schemes: -Click Add button -Choose Category and Date -Click Save Button -REcord Saved successfully and -Delete the record -received "[object Object]" and "Govt Schemes Inactive successfully" -Data shows on Grid | Fail | Low | Minor |  |  |  |  | Open |  | Closed |  | vadivu | 2021-05-10
KINDLY USE NEW CASE SHEET FOR TEST CASES MORE THAN 2998 NUMBERS (BEYOND THIS LINE)

## Trend_Charts
Test Result
Result | Number of Test Cases | Percentage
Pass | 0
Fail | 30 | 100%
To Do | 0
N/A | 0
CNT | 0
Total | 30 | 100%
Defect Priority
Priority | Number of Defects | Percentage
High | 0
Medium | 0
Low | 30 | 100%
Total | 30 | 100%
Defect Severity
Severity | Number of Defects | Percentage
Critical | 0
Major | 0
Minor | 30 | 100%
Total | 30 | 100%
Bug Status
Status | Number of Defects | Percentage
Open | 30 | 100%
Closed | 0
Justified | 0
Deferred | 0
Reopen | 0
Total | 30 | 100%
Phase Attributed
Phase | Number of Defects | Percentage
Front-End | 0
DataBase | 0
Planning | 0
Requirement | 0
Design | 0
Coding | 0
Total |  | 0%
Defect Type
Defects Type | Number of Defects | Percentage
Ambiguous | 0
Attribute | 0
Compilation | 0
Convention | 0
Incomplete | 0
Incorrect | 0
Interface | 0
Logical | 0
Memory | 0
Wrong Assignment | 0
Total |  | 0%

## Test_Summary_Charts
Test Summary Report
Test Lead Name :
Tester #1 Name :
Tester #2 Name :
Actual Test Completion Date:
Test Result Trend
Status | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Pass
Fail
To Do
N/A
CNT
Test Priority Trend
Priority | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
High
Medium
Low
Test Severity Trend
Severity | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Critical
Major
Minor
Test Bug Status Trend
Status | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Open
Closed
Justified
Deferred
Reopen
Test Phase Attribution Trend
Phases | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Planning
Requirement
Design
Coding
Test Defect Type Trend
Defects Type | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Ambiguous
Attribute
Compilation
Convention
Incomplete
Incorrect
Interface
Logical
Memory
Wrong Assignment